## Daily Status Update
Date: | 2015-02-23
Name: | Chris Redgrave
Tasks Planned for Today:
Task Name |  | %Complete | Notes:
The table definitions are aligned with Standard Interface Definition: list of columns, names, data type, sizes and nullable. |  | 20
Implement process to load data for any new/existing market without changes to ETL based on designed metadata model |  | 90 | Currently Testing This - should complete by COB 23/02/2015
Write mapping for each source file type |  | 80
Tasks Planed for Tomorrow:
Task Name |  | %Complete | Notes:
Miscellaneous Work:
Task Name |  | Notes:
Set-up local laptop to access VM |  | Complete
Add Region CD and DESC columns in Account Manager Table; Similarly change Type column to Role CD and DESC |  | Complete
Confirm that the require Reference tables are created and used. |  | Complete
Ensure that all the tables have custom columns: Local Market Ingestion Month Creation Date Valid From and To Current YN All MUST be NOT NULL Except VALID TO; VALID FROM / TO and CURRENT YN are only for Dimensions. Ensure that all REF DATA columns are added to the dimensions as a pair i,e, CD and DESC column e.g. Opportunity Status. |  | Complete
Add custom placeholder columns to the following tables: KPI Performance - 50 Opp Dimension - 25 Landscape - 50 |  | Complete
Risks & Issues:
Description |  | Type | Notes: