## Daily Status Update
Date: | 2015-02-26
Name: | Chris Redgrave
Tasks Planned for Today:
Task Name |  | %Complete | Notes:
Dimensions - D_OPPORTUNITY_DETAIL |  | 90 | Completed development but needs testing
Dimensions - D_LANDSCAPE_DETAIL |  | 50
Facts - F_OPPERTUNITY_M |  | 90 | Completed development but needs testing
Facts - F_LANDSCAPE_M |  | 50
Tasks Planed for Tomorrow:
Task Name |  | %Complete | Notes:
Dimensions - D_OPPORTUNITY_DETAIL |  | 100 | Complete Testing
Facts - F_OPPERTUNITY_M |  | 100 | Complete Testing
Dimensions - D_LANDSCAPE_DETAIL |  | 80 | Complete Development with Unit Testing to finish off
Facts - F_LANDSCAPE_M |  | 80 | Complete Development with Unit Testing to finish off
Miscellaneous Work:
Task Name |  | Notes:
Risks & Issues:
Description |  | Type | Notes: