## Sheet1
Dimension/Fact Name | Resource | Completion % | Notes
D_ACCOUNT_MANAGER | GE | 80% | Need to make changes based on latest changes to standard interface
D_CALENDAR_MONTH | GE | 100%
D_LOCAL_MARKET | CR | 100%
D_KPI_CALCULATION | GE | 90%
D_OPPORTUNITY_DETAIL | CR | 90%
D_LANDSCAPE_DETAIL | CR | 50%
F_REVENUE_M | CR | 0%
F_REVENUE_TARGET_M | CR | 0%
F_REVENUE_FORCAST_M | GE | 0%
F_OPPORTUNITY_M | CR | 90% | Started as this has to be mapped at the same time as the dimension as we have no BK for this data
F_LANDSCAPE_M | CR | 50% | Started as this has to be mapped at the same time as the dimension as we have no BK for this data
F_KPI_CALCULATIONS | GE | 0%