## Daily Status Update
Date: | 2015-02-24
Name: | Chris Redgrave
Tasks Planned for Today:
Task Name |  | %Complete | Notes:
The table definitions are aligned with Standard Interface Definition: list of columns, names, data type, sizes and nullable. |  | 80
Implement process to load data for any new/existing market without changes to ETL based on designed metadata model |  | 100 | Currently Testing This - should complete by COB 23/02/2015
Write mapping for each source file type |  | 95 | Landscape, Opportunity and Sales Professional to be altered in line with standard interface changes.
Write mappings to load changeable dimensions |  | 20 | Completed Mappings for D_CALENDAR_MONTH and D_LOCAL_MARKET
Tasks Planed for Tomorrow:
Task Name |  | %Complete | Notes:
Write mappings to load changeable dimensions |  | 40
The table definitions are aligned with Standard Interface Definition: list of columns, names, data type, sizes and nullable. |  | 100
Implement Changes to Data Model (Opportunity and Landscape) |  | 100
Update Data Model and Send to Muhammad and Simon for Review |  | 100
Miscellaneous Work:
Task Name |  | Notes:
Risks & Issues:
Description |  | Type | Notes: