## DateChart
Task No. | Key milestones (For) |  | Priority | Status | Weeks per task | Days | Weeks per phase | Start Date | Owner | Assigned To | Planned End Date | Actual End Date | Owner/Assist | Latest Update | Updates / Comments
1 | Create KPI GUIDANCE tables in Staging and Mart | Data Model & ETL | High | In Progress |  |  |  |  | GE | GE | 2015-02-19 |  |  | 20/02/2015: GE: Table created in DWH. Integrated into RPD and testing in progress. | < 19/02/2015: Geouffrey will do some of the tasks while majority are for Chris < 20/02/2015: GE: Table created in DWH. Integrated into RPD and testing in progress.
2 | Update KPI Performance table to add two columns: Total No of OPEN_STUCK and _OPEN_STALE | Data Model & ETL | High | In Progress | 69.4286 | 486 |  | 2013-10-21 | GE | GE | 2015-02-19 |  | AM | 24/02/2015: Geouffrey has discussed with Chris and agreed to make the required change | < 24/02/2015: Geouffrey has discussed with Chris and agreed to make the required change
3 | Ensure that all the tables have custom columns: Local Market Ingestion Month Creation Date Valid From and To Current YN All MUST be NOT NULL Except VALID TO; VALID FROM / TO and CURRENT YN are only for Dimensions. Ensure that all REF DATA columns are added to the dimensions as a pair i,e, CD and DESC column e.g. Opportunity Status. | Data Model & ETL | High | Closed | 70.5714 | 494 |  | 2013-10-17 | CR | CR | 2015-02-23 |  | AM | 25/02/2015 CR: Completed. | < 23/02/2015: MS: CR has informed that design is complete; implementation will be done tomorrow. < 25/02/2015 CR: Completed.
4 | The table definitions are aligned with Standard Interface Definition: list of columns, names, data type, sizes and nullable. | Data Model & ETL | High | Closed |  |  |  |  | CR | CR | 2015-02-23 |  |  | 25/02/2015 CR: Complete | < 23/02/2015: MS: CR has informed that design is complete; implementation will be done tomorrow. < 24/02/2015: CR: 80% Complete <25/02/2015 CR: Complete
5 | Confirm that the require Reference tables are created and used. | Data Model & ETL | High | Closed |  |  |  |  | CR | CR | 2015-02-23 | 2015-02-23 |  | 23/02/2015: MS: CR has confirmed that changes - so task can be closed. | < 23/02/2015: MS: CR has confirmed that changes - so task can be closed.
6 | Add Region CD and DESC columns in Account Manager Table; Similarly change Type column to Role CD and DESC | Data Model & ETL | High | Closed |  |  |  |  | CR |  | 2015-02-23 |  |  | 24/02/2015: CR: Completed | < 23/02/2015: MS: CR has informed that design is complete; implementation will be done tomorrow. < 24/02/2015: CR: Completed
7 | Set-up local laptop to access VM | Miscellenious | High | Closed |  |  |  |  | GE | GE | 2015-02-18 | 2015-02-18 |  | 18/02/2015: MS: Set-up is complete and using VM now. | < 18/02/2015: MS: Set-up is complete and using VM now.
8 | Set-up local laptop to access VM | Miscellenious | High | Closed |  |  |  |  | CR | CR | 2015-02-18 |  |  | 23/02/2015: MS - CR has reported that ODI agent is now installed and this task is complete | < 18/02/2015: MS: ODI Agent completion is pending; otherwise using VM for development work. < 23/02/2015: MS - CR has reported that ODI agent is now installed and this task is complete
9 | Using KPI Reference table for base values | Reports & Dashboards | High | In Progress |  |  |  |  | GE | GE |  |  |  | 20/02/2015: GE: Please elaborate on this item??? | < 20/02/2015: GE: Please elaborate on this item???
10 | Dynamically calculating YTD and Index (ranking report) values | Reports & Dashboards | Medium | Closed |  |  |  |  | GE | GE |  | 2015-02-20 |  | 20/02/2015: GE: Done | < 20/02/2015: GE: Done
11 | Add (FY, INR M) with title for all the numeric columns in Team Summary Report when generated for India only. | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE
12 | Review and update Standard Interface | Data Model & ETL | High | In Progress |  |  |  |  | SPM&C | MS | 2015-02-16 |  |  | 20/02/2015: MS: updated baseline version is published. | < 18/02/2015: The Standard Interface was expected to be reviewed and finalised by 16th but still being worked at. It is not with MS to review and make required changes. < 20/02/2015: MS: updated baseline version is published.
13 | provided first converted data feed in agreed format by 20th Feb; and finalise conversion by 25th Feb | Data Model & ETL | High | In Progress |  |  |  |  | SPM&C | SPM&C | 2015-02-25
14 | Provide final SPM&C dashboard homepage design by 18th Feb | Reports & Dashboards | Medium | In Progress |  |  |  |  | SPM&C | GE | 2015-02-18 |  |  | 18/02/2015: Geouffrey has agreed draft design for home page with SPM&C team. For more details see his email (Re: Landing Page) on 18/02 | < 18/02/2015: Geouffrey has agreed draft design for home page with SPM&C team. For more details see his email (Re: Landing Page) on 18/02
15 | How we can determine unique or different Landscape records. | Data Model & ETL | Medium | Closed |  |  |  |  | CR | CR | 2015-02-19 |  |  | 19/02/2015: Tom has advised that we don't need to do that though we need to identify records assigned to a AM which we can do by filtering on Account Manager Name attribute. | < 19/02/2015: Tom has advised that we don't need to do that though we need to identify records assigned to a AM which we can do by filtering on Account Manager Name attribute.
16 | Can corporate users access the solution deployed using VM | Infrastructure | Medium | In Progress |  |  |  |  | MS
17 | User Authentication: Where will the users of this system be located. Will they all be on the Vodafone Corporate network and able to connect to the server on the same network? If they are all on the same network we can consider integrating the VF Corporate authentication service for OBIEE authentication. Implementing this will allow users to log onto the system using their standard *@vodafone.com credentials. It also makes it a bit easier bringing new users onto the system as they will most likely already have an account set up on the network. | Miscellenious | Medium | Closed |  |  |  |  | MS | SPM&C | 2015-02-25 | 2015-02-19 |  | Email on 19/02>: In reponse to your question, Vodafone Network is the same across all opcos and group functions. This means that when they are logged onto the network in Spain, they are logged onto the same Vodafone corporate network as someone working in Group here in London. | < 19/02/2015: MS: Email sent to Tom to find out more about user authentication. < 20/02/2015: MS: Tom has advised <Email on 19/02>: In reponse to your question, Vodafone Network is the same across all opcos and group functions. This means that when they are logged onto the network in Spain, they are logged onto the same Vodafone corporate network as someone working in Group here in London.
18 | Scheduling PDF reports and emails: Two things here... * Do we have the correct sign-off from a security and business point of view that we are allowed to email sensitive information automatically. * We will need to following details in order to configure the emailing in OBIEE: SMTP Server Port UserName (If required by server) Password (If required by server) Display Name of Sending Email Address of Sender | Miscellenious | Low | Not Started |  |  |  |  | MS | MS
19 | Add custom placeholder columns to the following tables: KPI Performance - 50 Opp Dimension - 25 Landscape - 50 | Data Model & ETL | High | Closed |  |  |  |  | CR | CR | 2015-02-23 |  |  | 24/02/2015: CR: Completed | < 23/02/2015: MS: CR has informed that design is complete; implementation will be done tomorrow. < 24/02/2015: CR: Completed
20 | Esnure that the table names follow the naming conventions: Dimonsion D_<name> Fact F_<name>_D/M/Y to show the granularity | Data Model & ETL | High | Closed |  |  |  |  | CR | CR | 2015-02-23 |  |  | 24/02/2015: CR: Completed | < 24/02/2015: CR: Completed
21 | Implement Dimension as Type 2, but ensure that we still are able to find the state of detail record for a given month | Data Model & ETL | Medium | In Progress |  |  |  |  | CR | CR | 2015-02-23 |  |  | 20/02/2015: MS: Let's discuss before you make any progress with this | < 20/02/2015: MS: Let's discuss before you make any progress with this
22 | The data model MUST support the following: - Local Market Identifieable - Enable Security at Local Market, Individual AM level | Data Model & ETL | High | In Progress |  |  |  |  | CR | CR | 2015-02-24
23 | Enable User Login Audit | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-25 |  |  | 20/02/2015: GE: This will require about 2 days for congiguration | < 20/02/2015: GE: This will require about 2 days for congiguration
24 | Change All Staff to Hyperlinked entries like Ranking Report | Reports & Dashboards | High | Closed |  |  |  |  | GE | GE | 2015-02-23 |  |  | 24/02/2015: GE: All dashboards using this now | < 20/02/2015: GE: Ongoing while re-building dashboards < 24/02/2015: GE: All dashboards using this now
25 | Freeze the first column to make it visible all the time | Reports & Dashboards | High | In Progress |  |  |  |  | GE | GE | 2015-02-23 |  |  | 20/02/2015: GE: Looking into this | < 20/02/2015: GE: Looking into this
26 | Set the default focus to show Current Months variance | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-23
27 | Make each month a complete and separated block | Reports & Dashboards |  | Closed |  |  |  |  | GE | GE | 2015-02-23 |  |  | 24/02/2015: GE: Could not completely separate them but showed to SPMC team and they are happy with current view | < 23/02/2015: Separate blocks will cause performance issues. Trying to find single solution < 24/02/2015: GE: Could not completely separate them but showed to SPMC team and they are happy with current view
28 | Add return button on top | Reports & Dashboards | Medium | Closed |  |  |  |  | GE | GE | 2015-02-23 |  |  | 23/02/2015: MS: Duplicate | < 23/02/2015: MS: Duplicate
29 | Correct spellings on the drilldown version e.g. Opportunity Stat | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-23
30 | Need to test reports on all browsers - SPM&C team will provide the list including latest version | Reports & Dashboards | High | Not Started |  |  |  |  | SPM&C | SPM&C | 2015-02-25
31 | Include logged in user direct reporting line instead of All Staff hierarchy | Reports & Dashboards | High | Closed |  |  |  |  | GE | GE | 2015-02-25 |  |  | 23/02/2015: All reports now use this feature | < 23/02/2015: All reports now use this feature
32 | Merge multiple Team Summary reports into 1, if possible. | Reports & Dashboards | High | Closed |  |  |  |  | GE | GE | 2015-02-25 | 2015-02-24 |  | 24/02/2015: Done as much as can be done. All remaining ones are required for formatting requirements | < 24/02/2015: Done as much as can be done. All remaining ones are required for formatting requirements
33 | Merge multiple Individual Summary reports | Reports & Dashboards | High | In Progress |  |  |  |  | GE | GE | 2015-02-25
34 | Export detail reports to Excel | Reports & Dashboards | Low | Not Started |  |  |  |  | GE | GE | 2015-02-25
35 | Freeze First Column | Reports & Dashboards | High | In Progress |  |  |  |  | GE | GE | 2015-02-25
36 | Move Return button to top of page (Is this really necessary with breadcrumbs in 11.1.7?) | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-25
37 | Highlight entire row when mouse hover over any cell. | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-25
38 | Navigate from Ranking report to equivalent Individual PDF view. | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-25
39 | Change size of graph points | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-25
40 | Fix legend on graph when drilling to single item | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-25
41 | When open Team Summary Report - show that latest month and avriance | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-25
42 | Security: create admin users who have access to all data especially enable them to create Individual PDF reports | Reports & Dashboards | High | Not Started |  |  |  |  | GE | GE | 2015-02-26
43 | Ensure that Report displays are %: all core KPIs Items on Ranking report | Reports & Dashboards | High | Closed |  |  |  |  | GE | GE | 2015-02-23 |  |  | 24/02/2015: GE: Ensured that they are all using this value | < 24/02/2015: GE: Ensured that they are all using this value
44 | User Access: How we can get access for development and operational team members? Use of Managed Files Transfer: The solution requires participating local markets to send data feeds as CSV file using File Server. I understand that we can use Managed File Transfer Mechanism to achieve this. So wondering if there are any pre-requisites to use this? Backup & Recovery: How the backup and recovery will be managed and who will be responsible for this? Automatic Emailing of Reports: The solution is expected to automatically email generated reports. Is this possible from VM. If yes, do we need to request separately SMPT server set-up or firewall opening etc.? OpEx Charges: I am assuming that VT-IS will provide ongoing VM support. So wondering if the solution has to pay OpEx charges for that. If yes, will this be included in the VROM from VT-IS? Application deployment: Once VM is ready can the project team access that and migrate code to it or we have to engage some other e.g. Global Application team for this? Remedy Enabled Operational Support: - IS the Ops Support remedy enabled? If yes, who is the Remedy team we can engage with? | Infrastructure | High | Not Started |  |  |  |  | MS | MS | 2015-02-24
45 | Review Solution Design with Simon: Feedback from discussion with Peter and Jeff | Miscellenious | High | In Progress |  |  |  |  | MS | MS |  |  |  | 23/02/2015: MS: session took place today as planned and discussed the items. Simon Suggested to ask for approval from SteerCo if we have to go with Snapshot option for Dimensional data. | < 20/02/2015: MS: Meeting booked on Monday 23/02 < 23/02/2015: MS: session took place today as planned and discussed the items. Simon Suggested to ask for approval from SteerCo if we have to go with Snapshot option for Dimensional data.
46 | Data Validation: Review Standard Interface File and apply the Validation: For Opps feed only reject a record if Opp Owner and CUSTOM is not populated For Landscape feed only reject a record if Again Owner and CUSTOMER attributes information is not provided. For all other feeds use Nullable column value for validation. | Data Model & ETL | High | Closed |  |  |  |  | CR | CR | 2015-02-25 |  |  | 25/02/2015 CR: Implemented in the ODI Model | < 20/02/2015: MS: Let's discuss before you make any progress with this < 25/02/2015 CR: Implemented in the ODI Model
47 | On Ranking and Graph reports display Logged In user Name as a title or lable. | Reports & Dashboards | Medium | Not Started |  |  |  |  | GE | GE | 2015-02-25
48 | Both Ranking and Graph reports when clicked on to drill down the display moves to left - adjust to keep it to the centre | Reports & Dashboards | High | Not Started |  |  |  |  | GE | GE | 2015-02-25
49 | Request System Access for Muhammad to Rittman Systems: - JIRA - DB | Miscellenious | Medium | In Progress |  |  |  |  | MS | GE | 2015-02-23 |  |  | 23/02/2014: Requested from RM helpdesk. | < 23/02/2015: MS: Emailed to Geouffrey and Chris < 23/02/2014: Requested from RM helpdesk.
50 | Get sign-off of data model from Simon Dimaline | Data Model & ETL | High | In Progress |  |  |  |  | CR | CR | 2015-02-25 |  |  | 25/02/2015 CR: Will send at End of Play today. | < 25/02/2015 CR: Will send at End of Play today.
51 | Get Sign-off from Priyanthi for RPD | Reports & Dashboards | High | In Progress |  |  |  |  | MS | MS | 2015-02-20 |  |  | 20/02/2015: MS: review session held at 4:30 and showed the RPD to Priyanthi. She has not raised any concerns or suggested any changes. She will send the confirmation email later. | < 20/02/2015: MS: review session held at 4:30 and showed the RPD to Priyanthi. She has not raised any concerns or suggested any changes. She will send the confirmation email later.
52 | Finalise the Sales Professional data model design. | Data Model & ETL | High | Not Started |  |  |  |  | CR | CR | 2015-02-24
53 | Finalise Opportunity and Lanscape data validation design. | Data Model & ETL | High | Not Started |  |  |  |  | CR | CR | 2015-02-25
54 | Explore how we can dynamically do the following: - Show only selected attributes on drilldown report based on selected Local Market - How we can change the attribute titles based on the selected attributes. | Reports & Dashboards | High | Not Started |  |  |  |  | GE | GE | 2015-02-25
55 | Book demo session with Group Technology | Miscellenious | High | Not Started |  |  |  |  | MS | MS | 2015-02-27
56 | Confirm for the NL Sales Professional data, SPM&C team has provided an additional row per SM - see Design Decision Notes. | Data Model & ETL | High | Not Started |  |  |  |  | MS | MS | 2015-03-02
57 | Update Sale's Professional Interface definition based on discussion and agreement with SPM&C team. | Data Model & ETL | High | Closed |  |  |  |  | CR | CR | 2015-02-24 |  |  | 25/02/2015 CR: Complete. | < 24/02/2015: CR: In Progress. Tom will send over latest interface definition today for review. < 25/02/2015 CR: Complete.
58 | Chris to send Latest Data Model design and SQL Scripts for review to Muhammad | Data Model & ETL | High | Closed |  |  |  |  | CR | CR | 2015-02-25 |  |  | 25/02/2015 CR: Completed early this afternoon. | < 25/02/2015 CR: Completed early this afternoon.
59 | Chris to provide details of work split between him and Geouffrey included what is already completed in this task - Dimension mapping | Data Model & ETL | High | In Progress |  |  |  |  | CR | CR | 2015-02-25 |  |  | 25/02/2015: MS: due to Geouffrey's illness, it is agreed that Chris will work on the full task. We will assign a different task to Geouffrey when he is back. | < 25/02/2015: MS: due to Geouffrey's illness, it is agreed that Chris will work on the full task. We will assign a different task to Geouffrey when he is back.
60 | Chris to email and agree with Simon Dimaline to get agreement on: - For now we can use our own created reference data if common set is not available | Data Model & ETL | High | Not Started |  |  |  |  | CR | CR | 2015-02-26
Legend:
Not Started | Task not started yet
In Progress | Work in progress
Closed | Approved by IDMG, where required; no more work
Note on Q1: Saleem, Muhammad (UK Guildford): Always enter comment following below: < 19/02/2015: comments

## Ref Data
Not Started
In Progress
Closed
Muhammad Saleem | MS
Chris Redgrave | CR
Geouffrey Erasmas | GE
SPM&C
Data Model & ETL
Reports & Dashboards
Miscellenious
Infrastructure
High
Medium
Low