## Daily Status Update
Date: | 2015-03-05
Name: | Chris Redgrave
Tasks Planned for Today:
Task Name |  | %Complete | Notes:
Documentation - Migrating ODI |  | 40 | Complete First Draft
Migrate Code to Local Laptop |  | 100
Unit Testing ‘Real’ Data |  | 50 | Managed to process a full load of South Africa Data Successfully along with some Landscape data from New Zealand. I will Email the database dump to Geouffrey as soon as I can!
Tasks Planed for Tomorrow:
Task Name |  | %Complete | Notes:
Documentation - Migrating ODI |  | 100
Unit Testing ‘Real’ Data |  | 75 | Migrate a few additional markets to improve the demo data.
Miscellaneous Work:
Task Name |  | Notes:
Risks & Issues:
Description |  | Type | Notes: