## Daily Status Update
Date: | 2015-02-26
Name: | Chris Redgrave
Tasks Planned for Today:
Task Name |  | %Complete | Notes:
F_REVENUE_FORECAST |  | 100 | Completed and Unit Tested
Load Plan & Scheduling |  | 90 | Waiting on the completion of the F_KPI_PERFORMANCE_M mapping to be completed. We are also currently unable to complete the schedule so that it Emails on Error/Success as we do not have email server configuration information - the framework for this is in place but is currently deactivated.
Tasks Planed for Tomorrow:
Task Name |  | %Complete | Notes:
Load Plan & Scheduling |  | 100
Migrate Code to Local Laptop |  | 100
Unit Testing |  | 30 | Will start the Unit Testing on the RMC VM and then Migrate to the Local Laptops for Unit Testing with ‘real’ data.
Documentation - Loading Markets |  | ? | I will start this if I cannot continue unit testing as this is dependant on Tom/Kas giving us sample data.
Miscellaneous Work:
Task Name |  | Notes:
Risks & Issues:
Description |  | Type | Notes: